## Sheet1
ISSUE TRACKER
DASHBOARD
Project Name |  |  |  | High | Medium | Low | Total | %
Dental Case Tracker Pro |  |  | Closed | 52 | 92 | 35 | 179 | 91.33%
Office |  |  | In Progress | 3 | 3 | 1 | 7 | 3.571%
|  |  | Not Started | 0 | 7 | 2 | 9 | 4.592%
|  |  | Retest | 0 | 1 | 0 | 1 | 0.5102%
Project Owner |  |  | Total | 55 | 103 | 38 | 196
Jason Hochwender |  |  | % | 28.06% | 52.55% | 19.39%
# | ISSUE | DESCRIPTION | PRIORITY | DEPARTMENT | INITIATOR | STATUS | OPENED ON | CLOSED ON
169 | Test | Verify cross-browser compatibility (Firefox, Safari, Edge) | Medium |  |  | Retest
180 | Login | Keeps the login with email section expanded and it's driving me nuts | Low |  |  | Closed
148 | Test | Verify remember me functionality persists across browser restarts | Medium |  |  | Closed
177 | Login | After resting my password and clicking sign in, instead of taking me to the login page I am taken to the landing page | Low |  |  | Closed
178 | Login | After logging in with jason.hochwender@gmail.com, no profile pic shws up in the upper right hand corner | Low |  |  | Closed
179 | Misc | When logged in, if I turn off wifi or otherwise lose connection I get weird errors that pop up that say things like failed to fetch | Low |  |  | Closed
181 | Cases | Need to verify concurrent handling of cases | High |  |  | Closed
182 | Session | Need to warn of session timeout | Medium |  |  | Closed
183 | Plans | Need to revist trial expiration as I am not sure its working and if it is I am not sure all things are disabled (Insights) and I am not seeing any messaging | High |  |  | Closed
185 | HIPPA | Are we capturing everything we need to capture | High |  |  | Closed
186 | HIPAA | Do we have any data retention policies and if not do we need them | Medium |  |  | Closed
187 | Errors and Logging | Can we use our 404 page for all 404 page errors | High |  |  | Closed
189 | Cases | When I move a case backward I think I should be seeing notification of that | High |  |  | Closed
191 | Backups | Backup is on, create new case with attachments, get this error: Failed to create case: Google Drive backup is enabled but Google Drive is not connected. Please connect Google Drive from Settings or disable backup. | High |  |  | Closed
192 | Attachments | I should be able to add multiple attachments from different folders | Medium |  |  | Closed
194 | Attachments | Should I be able to click and view an attachment from the edit case screen? | Medium |  |  | Closed
195 | Printing | Should each attachment be on its own page? | Medium |  |  | Closed
196 | Cases | When removing attachments from a case on the edit case modal, if I close the modal before saving I don't get prompted to save changes | Medium |  |  | Closed
1 | Long load times | Loading the application takes > 30 seconds causing time out issues | High |  |  | Closed
2 | Settings menu | Remove dividers in menu | Low |  |  | Closed
3 | Dev case creation | Dev test data creation is timing out | Low |  |  | Closed
5 | Walk through | Add walkthrough/over view for first time visitors | Medium |  |  | Closed
6 | Contact Us Page | Clean up contact us page (i.e. icons) | Low |  |  | Closed
7 | Billing | Add stripe billing | Medium |  |  | Closed
8 | Delivered status | Remove cases in the delivered status after x number of days | Medium |  |  | Closed
9 | Settings modal | Add a cancel button to the settings modal | Low |  |  | Closed
10 | Admin functions | Set admin functionality in the settings menu | Medium |  |  | Closed
11 | Drag and Drop loading | Add a loading indicator when doing drag and drop | Medium |  |  | Closed
12 | No actions during a loading state | Ensure no keyboard shortcuts or other actions during loading | Medium |  |  | Closed
13 | Order of buttons in modal | Switch the order of the save and cancel buttons in the modal | Low |  |  | Closed
14 | Capture useage activity | Ensure we are capturing all changes of status etc | Medium |  |  | Closed
15 | Filter UX | Improve the UX of the filter functionality including removal of the dates | Medium |  |  | Closed
16 | Double click to edit | Trigger editing of a case by a double click | Low |  |  | Closed
17 | Consistent modal experience | The modals should all behave the same including button positioning, functionality etc | Low |  |  | Closed
18 | Enter key in create case | The enter key should trigger the create case modal | Low |  |  | Closed
19 | Speed up drag and drop | The drag and drop functionality is way too slow. | Medium |  |  | Closed
20 | Code cleanup | Make sure unused code is removed and remaining code is thoroughly commented | Medium |  |  | Closed
21 | Testing | Complete end-to-end testing including perf testing | High |  |  | Closed
22 | File attachments | Need view/download capability | High |  |  | Closed
23 | Revision history | Add revision history to cases when in edit mode | High |  | ` | Closed
24 | Revision history | Make revision history more thorough and detailed | Medium |  |  | Closed
25 | File attachment issue | Ensure multiple files can be added to each section | High |  |  | Closed
26 | Timeout | Need to handlethe timeout more gracefully | Low |  |  | Closed
27 | Allow archiving | Allow archiving of individual cases should be checked by default | Low |  |  | Closed
28 | View archeived | Need an option to view the archeived cases | Medium |  |  | Closed
30 | Print button | Move Archive button up and extend print across bottom | Low |  |  | Closed
31 | Billing tiers | Need to add billing tiers (Free, Standard, Pro) | High |  |  | Closed
32 | Editing while Printing | No editing of a case while it is in process of printing/generating | Medium |  |  | Closed
33 | Remove all debug code | Remove all debug code | Medium |  |  | Closed
34 | Improve Visual Design | I hate the current color scheme | High |  |  | Closed
35 | Default Status | Default to Origininated | Low |  |  | Closed
36 | Assigned To | Should not say Loading Users | Low |  |  | Closed
37 | Printed output | Printed output should be adjusted to fit the width | Medium |  |  | Closed
38 | Printed output issue w/PDFs | PDFs that are attached don't get printed properly | Medium |  |  | Closed
39 | Analytics tab | Add tabs to the main page including one for analytics | Medium |  |  | Closed
40 | Analytics tab | Add analytics and dashboard functionality | High |  |  | Closed
41 | Contact Us Page | Improve the visual design of the contact us page | Medium |  |  | Closed
42 | Encrypt DB | Ensure the db is as secure as fucking possible - encrypted, long password, etc | High |  |  | Closed
43 | Not seeing all users | I am missing from the assign to user list in the create case modal | High |  |  | Closed
44 | Lanes toolitip | The hint text in the manufactured lane is No cases in this stage. Which is different from the others. Same as Received From External Lab | Low |  |  | Closed
45 | Help Center | Need help center information | Low |  |  | Closed
46 | Help Center | Need live chat option | Low |  |  | Closed
47 | Drag and Drop | Drag and drop is way too slow | Medium |  |  | Closed
48 | Archived cases | Archived cases should have a minimum width | Low |  |  | Closed
50 | Revision Hhistory | Verify the revision history is capturing all events properly | High |  |  | Closed
51 | Plan pill | Update the plan pill including link when on the pro plan | Low |  |  | Closed
52 | Create case | Creating a case takes forever | High |  |  | Closed
53 | Create case | Close without saving functionality isn't working | Medium |  |  | Closed
54 | Create case | When creating a case, if there are errors, scroll back to the top | Low |  |  | Closed
55 | Walkthrough | First walkthrough slide is too close to the left edge as is the second one and the Analytics dashboard. The thrird one "Search Cases" - the View Archived Cases is on top of it a bit. | Medium |  |  | Closed
56 | Billing | Change pricing to $495 and $995 | High |  |  | Closed
57 | Billing | Change tiers to Evaluate, Operate, and Control | High |  |  | Closed
58 | Billing | No limited cases for evaluate - 30 days for everything | High |  |  | Closed
59 | Login | Need to create a landing page | High |  |  | Closed
60 | Case Movement | When draging, change case alignment based on drag direction | Low |  |  | Closed
62 | Login | Allow logging in with email instead of google | High |  |  | Closed
63 | Login | If logging in with email, save that option | High |  |  | Closed
64 | Adding users | Make sure that there is no gmal restrictions when adding someone | High |  |  | Closed
65 | Logging in as secondary user | Currently if a user is added to more than one practice, they get some kind of modal asking if they want to go to that practice or start a new one. Instead, if they are assigned to only one practice they should just proceed to that practice. If they are assigned to more than one practice, they should see a modal when they log in that tells them that they are added to more than one practice and then give them a way to select the one they want. | Medium |  |  | Closed
66 | Documentation | Create application documentation including architectural overview, functionality, build/release information | High |  |  | Closed
67 | Code Cleanup | Ensure code is commented and well organized | Medium |  |  | Closed
68 | Login | Add privacy policy and terms of service to google | High |  |  | Closed
69 | Billing | On the billing page make sure the information in the upper left hand corner is accurate and updated | High |  |  | Closed
70 | Cases | Add number of days in current case | High |  |  | Closed
71 | Activity Log | Make sure that case printing is included in activity log | High |  |  | Closed
72 | Adding users | If user is on the Operate plan and they have more than say 5 users (after switching from the evaluate plan) - show a message that says something like "This workspace exceeds typical Operate usage. Control unlocks full visibility and unlimited roles.Upgrade now". If they are on the operate plan and have < 5 users don't allow them to add more than 5. I would prefer this be something we can put in the appConfig so it can be changed easily | Medium |  |  | Closed
74 | Adding users | In the Practice Users and Roles section add an option so that the person added can be limited to just cases assigned to them | High |  |  | Closed
75 | Dev Tools | Make window slightly taller so I don't have to scroll | Low |  |  | Closed
76 | Archived cases | View record count on the View Archived Cases button | Medium |  |  | Closed
77 | Archived cases | When I click the archive button on an individual case, the total count needs to get updated | Medium |  |  | Closed
78 | Analytics tab | Delivered isn't working | Medium |  |  | Closed
79 | Billing Plan | User should NOT have access to the anlytics tab if they are on the Operate plan. Also, if user is on the Operate plan and they have more than 5 users (after switching from the evaluate plan) - show a message inline that says something like "This workspace exceeds typical Operate usage. Control unlocks full visibility and unlimited roles.Upgrade now". If they are on the operate plan and have < 5 users don't allow them to add more than 5. I would prefer the number of users to limit to is something we can put in the appConfig so it can be changed easily | High |  |  | Closed
80 | URL | Make sure www.dentatrak, dentrak.com, http://dentatrack.com, http://www.dentatrack.com, https://www.dentatrack.com and https://dentatrack.com all direct to dentatrak.com | High |  |  | Closed
81 | Adding users | If I type an email in and hit enter (i.e. I have focus in that field) it should trigger the add user button. If I have text in that field and click save at the button it should also add that user |  |  |  | Closed
82 | Adding users | The table header shouldn't be the same color as the ros below it. It needs to stand out just a bit more | Medium |  |  | Closed
83 | Labels | Limit the number of labels just like we would with users | High |  |  | Closed
84 | Tooltips | Tooltips need to be styled better | Low |  |  | Closed
85 | AI | Don't show AI recommendations on the analytics tab if there are no cases | Medium |  |  | Closed
86 | Backups | Disable "Backup case data to Google Drive" if the orignal creator does not have a google workspace account. Show verbiage inline that explains why | High |  |  | Closed
87 | Settings | Need to confirm with user when unsaved changes | Medium |  |  | Closed
88 | Logging | It looks like we might be duplicating things in the case log | High |  |  | Closed
89 | Login | Remove "Google Cloud Powered" | Low |  |  | Closed
90 | Login | Left Justify Email and Password on login with email. Do the same with the create account screen - first name, last name, email, password, and confirm password. | Medium |  |  | Closed
91 | Login | Update he background on the login screen | Low |  |  | Closed
92 | Analytics tab | We should't see stuff like these characters in the AI recommendations: With one case currently in the &#039;Designed&#039; status, implementing a formal design review process before proceeding to the next stage can help catch errors early, reducing remakes and improving the final quality of the bridge. This includes checklists and standardized criteria for design approval. | Medium |  |  | Closed
93 | Analytics tab | Add more widgets to the analytics dashboard for things like average time a case sits in each state. | Medium |  |  | Closed
94 | Mobile | Make login more mobile friendly | High |  |  | Closed
95 | Login | Need reset password functionality | High |  |  | Closed
96 | Cases | In status value is N/A | Medium |  |  | Closed
97 | Login | When signing in with email/password I am redirected but the login screen doesn't go away | High |  |  | Closed
98 | Login | Fields don't line up when creating new user | Medium |  |  | Closed
99 | Login | After I enter my first password, I then have to reenter it 2x? | High |  |  | Closed
100 | Login | Add verification link when users create an account via email/password | High |  |  | Closed
101 | Login | Need indicator on sign-in button when signing in with email/password | Medium |  |  | Closed
102 | Backups | The message is bad: Backup case data to Google Drive This feature requires Google Drive to be connected. Go to the Google Drive section below to connect your Google Drive account. It should say something like: In order to use this feature you must create your practice using a workspace account | High |  |  | Closed
103 | BAA | Need better required field messaging | Low |  |  | Closed
104 | Walkthrough | When first displaying the walkthrough jumps around | Low |  |  | Closed
105 | Archived cases | Add a "don't show this again" message and checkbox on the archive modal | Medium |  |  | Closed
106 | Code cleanup | Get rid of error log messages that were used for testing | Low |  |  | Closed
107 | Walkthrough | Enhance walkthrough to show the settings modal | Medium |  |  | Closed
110 | Login | Sencond Continue with Google button needs to be centered | Low |  |  | Closed
111 | Login | Signup with email is not sending the verification email in prod | High |  |  | Closed
112 | Dev tools | Message is messed up ⚠️ PRODUCTION ENVIRONMENT You are using dev tools in PRODUCTION. All changes will only affect your practice . Destructive actions require confirmation. | Low |  |  | Closed
113 | Dev Tools | Don't need clear cache or clear session or reload | Medium |  |  | Closed
114 | Settings | Tooltips on user header columns should not be all caps | Low |  |  | Closed
115 | Filters | Add an open to show only cases that are late | Low |  |  | Closed
117 | Filters | Searching by patient first name + last name doesn't work | High |  |  | Closed
118 | Filters | Late cases only checkbox doesn't do anything | High |  |  | Closed
119 | Cases | In status value is set for Today in Dev and it shows -1 in prod | High |  |  | Closed
120 | Printing | Printing is giving an error of "[29-Dec-2025 10:33:43 America/New_York] Google Drive: Not authenticated or token expired" | High |  |  | Closed
121 | Settings | The settings modal is telling me I have unsaved changes even if I just open and then immediately close the modal. | Medium |  |  | Closed
122 | Adding users | When trying to add a user that has already been added to a diiferent practice, I am seeing: This user is already a member of practice 'Premier Dental Implants' | High |  |  | Closed
123 | Data View | I am seeing data I don't think I should. | High |  |  | Closed
124 | Labels | When adding new labels, if I hit enter it should add the label and put focus back in the add lable field. Don't trigger the submit | High |  |  | Closed
125 | Create case | when I try and create a case I get errors: Failed to create case: {"success":false,"error":"Invalid action"}{"success":true,"message":"Case created successfully","caseData":{"patientFirstName":"Jason","patientLastName":"Hoch","patientDOB":"1970-04-30","dentistName": Also, now that we have changed how labels work we need to make sure that test case creation is updated to accomodate | High |  |  | Closed
126 | Tags | It's a little hard to remove a label from the individual cases | High |  |  | Closed
129 | Test | Verify password reset email is received and link works | Medium |  |  | Closed
130 | Test | Verify account verification email is received for new users | Medium |  |  | Closed
131 | Test | Verify print functionality for case details | Medium |  |  | Closed
132 | Test | Verify PDF export of case details renders correctly | Medium |  |  | Closed
133 | Test | Verify drag-and-drop works on actual touch devices (not emulated) | Medium |  |  | Closed
135 | Test | Verify app works offline and syncs when back online | Medium |  |  | Closed
136 | Test | Verify browser back/forward navigation works correctly | Medium |  |  | Closed
137 | Test | Verify deep linking to specific cases works | Medium |  |  | Closed
138 | Test | Verify copy/paste functionality in form fields | Medium |  |  | Closed
139 | Test | Verify right-click context menu behavior | Medium |  |  | Closed
140 | Test | Verify keyboard shortcuts work (if any exist) | Medium |  |  | Closed
141 | Test | Verify screen reader announces content correctly | Medium |  |  | Closed
142 | Test | Verify color contrast meets WCAG AA standards | Medium |  |  | Closed
143 | Test | Verify focus indicators are visible for keyboard users | Medium |  |  | Closed
144 | Test | Verify application works with browser zoom (not just text scaling) | Medium |  |  | Closed
145 | Test | Verify real-time updates appear when another user modifies a case | Medium |  |  | Closed
146 | Test | Verify concurrent editing conflict resolution | Medium |  |  | Closed
147 | Test | Verify session timeout warning appears before auto-logout | Medium |  |  | Closed
149 | Test | Verify SSO/OAuth login flow (Google, Microsoft) if supported | Medium |  |  | Closed
150 | Test | Verify 2FA authentication flow with authenticator app | Medium |  |  | Closed
151 | Test | Verify 2FA recovery codes work correctly | Medium |  |  | Closed
152 | Test | Verify billing/subscription page displays correct plan info | Medium |  |  | Closed
153 | Test | Verify payment processing works (Stripe integration) | Medium |  |  | Closed
154 | Test | Verify invoice generation and download | Medium |  |  | Closed
155 | Test | Verify plan upgrade/downgrade flow | Medium |  |  | Closed
156 | Test | Verify trial expiration handling | Medium |  |  | Closed
157 | Test | Verify data import from external systems | Medium |  |  | Closed
158 | Test | Verify data export produces valid file format | Medium |  |  | Closed
159 | Test | Verify bulk operations (select multiple cases, bulk archive) | Medium |  |  | Closed
160 | Test | Verify search results pagination | Medium |  |  | Closed
161 | Test | Verify browser autofill works correctly with forms | Medium |  |  | Closed
162 | Test | Verify application performance under slow network (3G) | Medium |  |  | Closed
163 | Test | Verify large file upload progress indicator | Medium |  |  | Closed
164 | Test | Verify image compression/optimization on upload | Medium |  |  | Closed
165 | Test | Verify HIPAA audit log captures all required events | Medium |  |  | Closed
166 | Test | Verify user activity logging for compliance | Medium |  |  | Closed
167 | Test | Verify data retention policies are enforced | Medium |  |  | Closed
168 | Test | Verify account deletion removes all user data | Medium |  |  | Closed
170 | Test | Verify application on actual iOS Safari | Medium |  |  | Closed
171 | Test | Verify application on actual Android Chrome | Medium |  |  | Closed
172 | Test | Verify help/documentation links work | Medium |  |  | Closed
173 | Test | Verify support chat/contact functionality | Medium |  |  | Closed
174 | Test | Verify error pages (404, 500) display correctly | Medium |  |  | Closed
175 | Test | Verify maintenance mode page displays when enabled | Medium |  |  | Closed
176 | Test | Verify Backup to Google Drive | Medium |  |  | Closed
179 | Lab Insights | The tooltips in the header of lab performance are all caps and have things like started_at. Also need to verify that its calculating those correctly | Medium |  |  | In Progress
180 | Resources | Need to update resources page for better catorization | Medium |  |  | In Progress
181 | Resources | Add tracking spreadsheet to resources page | Medium |  |  | In Progress
182 | Mobile | Update site for better mobile experience | Medium |  |  | Not Started
183 | Accessability | Make sure site is accessibile and ADA compliant | Medium |  |  | Not Started
184 | Internationalization | Add spanish | Medium |  |  | Not Started
185 | Notifications | Add notifications (email, app, text) | Medium |  |  | Not Started
186 | Secure Chat | Add secure chat | Medium |  |  | Not Started
187 | Resources | Update user guide | Medium |  |  | Not Started
188 | Resources | Translate user guide to spanish | Medium |  |  | Not Started
189 | Insights | Have a combined insights tab with sub tabs for practice and lab? | Low |  |  | In Progress
190 | Landing Page | Swap Pricing and Resources in menu | High |  |  | In Progress
191 | Login | Add HIPAA info | High |  |  | In Progress
192 | Landing Page | Make copy more compelling | High |  |  | In Progress
193 | Archived cases | Add Clear button to the filters | Low |  |  | Not Started
194 | Cases | Add tagging and filters by tag | Low |  |  | Not Started